## Sheet1
INTIMALS deliverables

Deliverables from WP0:
P0.1 Prototype of legacy software importer ©syntactic information¨ for the INTiMALS meta-model ( RL ; due end of M04)
R0.2 Report on the evaluation of INTiMALS’ support for mining coding conventions & idioms in legacy systems ( RL ; first draft due end of M07, final version due end of M12)
P0.3 Extension semantic information of the legacy software importer for the INTiMALS meta-model (RL ; end of M16)
R0.4 Report on the evaluation of INTiMALS’ support for mining usage patterns ( RL ; first draft due end of M19, final version due end of M24)
P0.5 Extension version information¨ of the legacy software importer for the INTiMALS meta-model ( RL ; end of M28)
R0.6 Report on the evaluation of INTiMALS’ support for edit patterns in UC3 ( RL ; first draft due end of M31, final version due end of M36)

Deliverables from WP1 (P=prototype, R=report, bold=task leader)
P1.1 Prototype implementation of the meta-model and an accompanying importer for syntactic information ( VUB , UCL, R; due M03)
P1.2 Prototype implementation of its representation for coding conventions & idioms ( UCL , VUB, RL; due end of M03)
P1.3 Extension of meta-model and importer with support for semantic information ( VUB , UCL, RL; due end of M15)
P1.4 Prototype implementation of its representation for usage patterns ( UCL , VUB, RL; due end of M15)
P1.5 Extension of meta-model and importer with support for change information ( VUB , UCL, RL; due end of M27)	P1.5b	Meta-model for mining patterns in 2-class data
P1.6 Prototype implementation of its representation for edit patterns ( UCL , VUB, RL; due end of M27)	P1.6b

Deliverables from WP2 (P=prototype, R=report, bold=task leader)		Note	VUB
P2.1 Frequent subgraph mining system for discovering patterns in attributed graphs, optimized for directed acyclic graphs ( UCL , VUB; due end of M06)	P2.1	FREQTALS algorithm
R2.2 Report on its application to mining for coding conventions & idioms in syntactic information represented according to the meta­model of P1.1 ( UCL , VUB; first draft due end of M06, final version due end of M12)	R2.2	FREQTALS evaluation
P2.3 Adaptation of the frequent subgraph mining algorithm to support usage patterns ( UCL , VUB; due end of M18)	P2.3b	P2.3b-miner-semantic-patterns-subdue	P2.3	P2.3-miner-semantic-patterns (BIG-GROUM)
R2.4 Report on its application to mining for usage patterns in semantic information represented according to the meta­model of P1.3 ( UCL, VUB; first draft due end of M18, final version due end of M24)	R2.4b	R2.4b-miner-semantic-patterns-subdue	R2.4	R2.4-evaluation-semantic-miner (BIG-GROUMS)
P2.5 Adaptation of the frequent subgraph mining algorithm to support edit patterns ( VUB, UCL; due end of M30)	P2.5b	P2.5b-mining-edit-patterns-from-different-versions	P2.5a	SysEdMiner ? Or student thesis
R2.6 Report on its application to mining for edit patterns in change information represented according to the meta-model of P1.5 ( VUB, UCL; first draft due end of M30, final version due end of M36)	R2.6b	R2.6b-evaluatate-mining-edit-patterns-from-different-versions	R2.6a	evaluate SysEdMiner ?
Additional Pattern Miner Evaluation (UCL, VUB, RL)	R2.2b	R2.2b-BENEVOL2019
Mining patterns in C# source code	R2.2c	-> 3.3
Mining patterns in Python source code	R2.6c	Writing → R0.6

Deliverables from WP3 (P=prototype, R=report, bold=task leader)
P3.1 Prototype offering assistance for program comprehension in the form of a browser for mined patterns ( RL , VUB, UCL; due M09).

P3.2 Prototype offering assistance for anomaly detection in the form of a browser for partial matches of mined patterns (UCL , VUB, RL; due M21)		???

P3.3 Prototype offering assistance for program modernisation in the form of edit recommendations that complete a partial match for a mined pattern ( VUB , UCL, RL; due M33)